# Project execution plan & timeline

Waiting: Deferral Without Denial · Stellenbosch University Graduate School Assemblies 2026
Convenor: Dr Bo Lyu · Modern Foreign Languages · bo@sun.ac.za
Site: https://deferralwithoutdenial.org
Status date: 1 September 2026

## 1. Objective

Deliver one in-person Assembly day in late October 2026, ending mid-afternoon under the proposed day schedule (sessions ±30–35 minutes; finish ±15:30), with:

- six theme sessions + staged waiting interludes

- open-call presenters / facilitators / audience

- print kit (posters, tickets, forms)

- documentary capture of the day

- post-event publication and video premiere on the site

Budget frame: R25 000 (Graduate School acceptance, 28 Aug 2026).

## 2. Proposed day schedule (compressed)

| Time | Item | Duration |
| --- | --- | --- |
| 09:00 | Prologue · The door | ±15 min |
| 09:15 | Opening frame | ±15 min |
| 09:30 | Session I · Waiting room of history | ±30–35 min |
| 10:05 | Interlude · The ticket | ±10 min |
| 10:15 | Session II · Papers | ±30–35 min |
| 10:50 | Tea · The form | ±25 min |
| 11:15 | Session III · Nobody signs a delay | ±30–35 min |
| 11:50 | Lunch · Canteen of deferral | ±55 min |
| 12:45 | Session IV · Penelopes | ±30–35 min |
| 13:20 | Interlude · Silent queue | ±10 min |
| 13:30 | Session V · The queue | ±30–35 min |
| 14:05 | Tea · Second sitting | ±20 min |
| 14:25 | Session VI · Art of waiting | ±30–35 min |
| 15:00 | Closing · The chair | ±15 min |
| 15:15 | Epilogue · Pending wall | ±15 min |
| ±15:30 | Day ends |  |

Live on site: /schedule · /experiment

## 3. Workstreams & owners

| Workstream | Lead | Supports |
| --- | --- | --- |
| Programme & presenters | Dr Bo Lyu | Grad School / dept chairs |
| Facilitators & day script | Prof. Catherine Du Toit (Research) + Bo | Drama / volunteers |
| Venue & AV | Bo + Faculty admin | Timetable office / campus bookings |
| Print & tickets | Bo / design kit | Campus print shop or external |
| Catering · mysterious food | Bo + facilitator team | Caterers / kitchen |
| Filmmaking / press | Open-call filmmaker | Press office if needed |
| Comms & open call | Bo | Site / email / FASS lists |
| Budget & claims | Bo | Grad School finance |
| Website & debate | Bo / technical | FormSubmit, Remark42 |

## 4. Timeline (from 1 Sep 2026)

### Phase A — Lock the call (1–8 Sep)

- Site live; open call published

- Push call through FASS / Grad School / departmental lists (daily until 8 Sep)

- Monitor FormSubmit → bo@sun.ac.za (check junk)

- Tue 8 Sep 2026 — presenter & facilitator responses close

- Audience registration remains open until the day

### Phase B — Confirm people & room (9–22 Sep)

- Shortlist presenters per theme; write confirmations (use Word template)

- Confirm facilitator roster and role cards (ticket desk, clerk, queue, chair)

- Confirm exact Assembly date within late October

- Book venue (capacity ≥ audience + presenters; breakout for tea desk & silent queue; AV)

- Confirm AV: projector, mic, recording power / lighting for film

- First pass programme PDF for Grad School / Faculty notice

### Phase C — Production design (23 Sep – 6 Oct)

- Finalise day script timings against room logistics

- Print quote: A3 posters (call + event), tickets, Application to Be Heard forms, pending-wall cards, door notices

- Order catering for “mysterious food” (numbered dishes, no menu; deferred servings)

- Confirm filmmaker / press; consent language already on take-part form

- Build presenter PPT decks from unified template

- Brief patrons / chairs with Word run-sheet

### Phase D — Pre-event fortnight (7–20 Oct)

- Send final programme + proposed schedule to all roles

- Print run complete; check tickets by role count

- Site visit: door, ticket desk, form desk, empty chair spot, pending wall surface

- Rehearse interludes (ticket draw, deferred stamps, silent queue, second sitting) — 60–90 min

- Confirm lunch logistics (lot trays; one unset place)

- Publish confirmed date/room on site (replace “late October / TBC”)

### Phase E — Assembly week (week of event)

- Mon–Tue: final headcount; print buffer; name cards if needed

- Day before: load-in props (forms, stamps, tickets, clock set wrong, OFFICE sign, chair)

- Assembly day: run proposed script; film; pending-wall harvest

- Day after: thank-you notes; expense claims; photo / clip for site

### Phase F — Afterlives (Nov–Dec 2026)

- Edit documentary; premiere on /video

- Collect papers / abstracts for /publication

- Keep /debate open; archive Assembly page with real names & photos

- Short report to Grad School (outcomes vs R25k)

## 5. Venue checklist

- Capacity and layout (theatre vs seminar; movable chairs for queue)

- Adjacent foyer or corridor for prologue door delay

- Table space for ticket desk + form desk

- Wall / board for pending forms and epilogue cards

- One prominent empty chair under light

- Catering access for numbered dishes

- Power for film + projection; blackout if needed

- Accessibility; toilets; fire exits noted on run-sheet

- Booking confirmation PDF filed in matter folder

## 6. Print checklist

From https://deferralwithoutdenial.org/print/

| Item | Qty (est.) | When to print | Notes |
| --- | --- | --- | --- |
| Open-call posters (choose 2–3) | 10–20 A3 | Now–mid Sep | Corridors / noticeboards |
| Event posters (choose 2–3) | 15–30 A3 | After date fixed | Campus + Faculty |
| Theme posters | optional | Oct | Room dressing |
| Role tickets | 1 per participant + 20 spare | 2 weeks before | By role colour/stub |
| Application to Be Heard forms | 80–120 | 1 week before | Tea · The form |
| Pending-wall cards | 80–120 | 1 week before | Epilogue |
| Door notice (“will begin shortly”) | 5 | Day before | Prologue |
| OFFICE sign | 1–2 | Day before | Silent queue |
| Run-sheets for facilitators | 10 | Week before | Word template |

## 7. People communication plan

| Audience | Message | Channel | Timing |
| --- | --- | --- | --- |
| Open-call prospects | Take part by 8 Sep | Email lists, site, posters | 1–8 Sep |
| Shortlisted presenters | Confirm theme, 30–35 min brief, honorarium | Email + Word letter | 9–15 Sep |
| Facilitators | Role assignment + rehearsal date | Email | Mid Sep + Oct |
| Patrons / chairs | Invitation + session brief | Email | Late Sep |
| Audience (who wait / family / officials) | Register; consent to experiment & film | Site form | Ongoing |
| Grad School / Faculty | Date, room, budget claim path | Formal note | After venue lock |
| Caterers | Mysterious food brief (numbers, lot, deferred) | Meeting + Word brief | Early Oct |
| Filmmaker | Shot list + consent | Meeting | Early Oct |
| All participants | Final programme ±15:30 end | Email + site | 7–10 days before |

Templates: templates/Deferral-Without-Denial-Template.docx · templates/Deferral-Without-Denial-Template.pptx

## 8. Risks & mitigations

| Risk | Mitigation |
| --- | --- |
| Thin open-call response by 8 Sep | Extend audience; personal follow-ups; keep June Luna practice slot for Theme III if needed |
| Venue clash in late Oct | Book by 22 Sep; hold 2 backup rooms |
| Sessions overrun | Hard chairing; 30–35 min rule on confirmation letters |
| Catering fails “mystery” brief | Written brief + tasting; numbered labels only |
| Film consent gaps | Form already includes consent; door reminder |
| Print delays | Place order ≥10 working days before; local shop backup |
| Budget overrun | Prioritise: room + food + print + honoraria; film as stretch |

## 9. Immediate next actions (this week)

- Blast open call to FASS / Grad School lists (deadline 8 Sep).

- Request late-October room holds from campus bookings (2–3 candidate dates).

- Ask print shop for A3 quote using /print/ call + event PDFs.

- Diary facilitator briefing once responses close.

- Copy PPT/Word templates into presenter confirmation pack.

Living document — update after 8 September shortlist and venue confirmation.